## Capstone - Detail
Date | Who | % complete |  | Event | Goal |  | 2017-10-01
2017-08-31 | M,B,P | 100 | 0 | Webinar |  | 31 |  | 0
2017-09-15 | M,B,P | 100 | 0 | 1630 Call with Rob
2017-09-17 | M,B,P | 100 | 0 | 1900 CST group call | Combine Notes on the Beta Draft
2017-09-18 | M,B,P | 100 | 0 | 1900 CST group call | Compile the beta draft ==> submit
2017-09-20 | M,B,P | 100 | 0 | beta draft due *
2017-09-24 | M,B,P | 100 | 0 | 1900 CST group call
2017-09-26 | M,B,P | 100 | 0 | online class discussions | receive feedback from others in class regarding the beta draft
2017-09-27 | M,B,P | 100 | 0 | online class discussions | must attend at
2017-09-28 | M,B,P | 100 | 0 | online class discussions | least one of these meetings
2017-10-01 | M,B,P | 0 | 3 | 1900 CST group call
2017-10-07 | M,B,P | 0 | 2 | Meet with advisors: Matteo (1400 CST, Skype)
2017-10-07 | M,B,P | 0 | 2 | Meet with advisors: Rob (not scheduled)
2017-10-08 | B | 0 | 2 | Ethics Write-Up: Write Drafts
2017-10-08 | M | 0 | 2 | Blockchain Write-Up: Write Drafts
2017-10-08 | M,B,P | 0 | 2 | Introduction Write-Up: Write Drafts
2017-10-08 | M,B,P | 0 | 2 | Introduction Write-Up: Drafts - redline
2017-10-08 | M,B,P | 0 | 2 | Introduction Write-Up: Drafts - Combine, finish
2017-10-08 | M,B,P | 0 | 2 | Abstract Write-Up: Write Drafts
2017-10-08 | M,B,P | 0 | 2 | Abstract Write-Up: Drafts - redline
2017-10-08 | M,B,P | 0 | 2 | Abstract Write-Up: Drafts - Combine, finish
2017-10-08 | M,B,P | 0 | 2 | 1900 CST group call
2017-10-08 | P | 0 | 2 | Data Write-Up: Write Drafts
2017-10-15 | M,B,P | 0 | 1 | Blockchain Write-Up: Drafts - redline
2017-10-15 | M,B,P | 0 | 1 | Data Write-Up: Drafts - redline
2017-10-15 | M,B,P | 0 | 1 | Ethics Write-Up: Drafts - redline
2017-10-15 | M,B,P | 0 | 1 | 1900 CST group call | Combine Notes on the First Draft
2017-10-15 | M,B,P | 0 | 1 | Meet with advisors
2017-10-22 | M,B,P | 0 | 1 | Blockchain Write-Up: Drafts - Combine, finish
2017-10-22 | M,B,P | 0 | 1 | Data Write-Up: Drafts - Combine, finish
2017-10-22 | M,B,P | 0 | 1 | Ethics Write-Up: Drafts - Combine, finish
2017-10-22 | M,B,P | 0 | 1 | 1900 CST group call | Compile the first draft ==> submit
2017-10-25 | M,B,P | 0 | 1 | First Paper Draft Due | at least eight pages expected
2017-10-29 | M,B,P | 0 | 1 | 1900 CST group call
2017-10-31 | M,B,P | 0 | 1 | online class discussions | receive feedback from others in class regarding the beta draft
2017-11-01 | M,B,P | 0 | 1 | online class discussions | must attend at
2017-11-01 | M,B,P | 0 | 1 | Meet with advisors
2017-11-02 | M,B,P | 0 | 1 | online class discussions | least one of these meetings
2017-11-05 | M,B,P | 0 | 1 | 1900 CST group call
2017-11-12 | M,B,P | 0 | 1 | 1900 CST group call
2017-11-15 | M,B,P | 0 | 1 | Meet with advisors
2017-11-19 | M,B,P | 0 | 1 | 1900 CST group call
2017-11-26 | M,B,P | 0 | 1 | 1900 CST group call
2017-12-01 | M,B,P | 0 | 1 | Meet with advisors
2017-12-03 | M,B,P | 0 | 1 | 1900 CST group call | Combine Notes on the Second Draft
2017-12-10 | M,B,P | 0 | 1 | 1900 CST group call | Compile the second draft ==> submit
2017-12-15 | M,B,P | 0 | 1 | Second Paper Draft Due | (points count towards Capstone B [5%]) 15-30 pages